## Summary
Askaan / Saqr — Non-Chargeable Work Orders (resolved by Injaaz MMR chargeable rules)
Contract | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | Total
A & F Tower-AC | 0 | 3 | 2 | 1 | 2 | 4 | 12
A & F Tower-MEP | 2 | 4 | 2 | 2 | 4 | 4 | 18
Al Andalous Tower 1-AC | 0 | 0 | 0 | 0 | 1 | 0 | 1
Al Andalous Tower 1-MEP | 2 | 2 | 7 | 3 | 4 | 1 | 19
Al Andalous Tower 2-AC | 0 | 0 | 1 | 0 | 0 | 0 | 1
Al Andalous Tower 2-MEP | 4 | 1 | 0 | 0 | 0 | 0 | 5
Al Andalous Tower 3-AC | 0 | 0 | 0 | 1 | 0 | 0 | 1
Al Andalous Tower 3-MEP | 2 | 1 | 1 | 0 | 1 | 1 | 6
Al Raffa 1-AC | 0 | 0 | 0 | 1 | 1 | 4 | 6
Al Raffa 1-Elevator | 0 | 0 | 0 | 0 | 0 | 1 | 1
Al Raffa 1-MEP | 1 | 1 | 1 | 2 | 3 | 0 | 8
Al Raffa 2-AC | 0 | 1 | 0 | 0 | 1 | 4 | 6
Al Raffa 2-MEP | 2 | 0 | 1 | 0 | 2 | 0 | 5
Al Shaali Building-AC | 0 | 0 | 1 | 0 | 1 | 1 | 3
Alia plaza-MEP | 1 | 0 | 1 | 2 | 3 | 0 | 7
Askaan office-LS | 0 | 0 | 2 | 1 | 1 | 1 | 5
C1 Tower-TFM | 17 | 7 | 25 | 31 | 12 | 18 | 110
Najim Building-AC | 0 | 0 | 0 | 1 | 1 | 2 | 4
Najim Building-MEP | 0 | 1 | 2 | 0 | 0 | 0 | 3
Nuiymeya 3-Elevator | 0 | 1 | 0 | 0 | 0 | 0 | 1
Nuiymeya 3-MEP | 0 | 0 | 0 | 1 | 0 | 0 | 1
Waqef 5-AC | 0 | 1 | 3 | 2 | 6 | 7 | 19
Waqef 5-MEP | 2 | 1 | 1 | 2 | 0 | 0 | 6
Total | 33 | 24 | 50 | 50 | 43 | 48 | 248

## Jan-2026
A & F Tower-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10015907 | 05-Jan-2026 | P3 | Carpenter works - Carpentry - Carpenter required | Askaan Properties LLC | 105-AF | Carpenter works | 02-Feb-2026 |  | Ramesh Rajak | Pending | A & F Tower-MEP | A&F Tower | Office No 105 | Non-Chargeable
10016532 | 28-Jan-2026 | P3 | Water Features - Plumbing - Plumbing issues | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Entrance/ Reception Area | Non-Chargeable
Al Andalous Tower 1-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10015829 | 03-Jan-2026 | P1 | Plumbing systems - Plumbing - Watchman room -Water leakage | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Entrance | Non-Chargeable
10015844 | 04-Jan-2026 | P3 | Electrical Works - Electrical - Electrician required | Askaan Properties LLC | Arshith Swaminath | Electrical Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Transfer Pump Room | Non-Chargeable
Al Andalous Tower 2-MEP — 4 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016067 | 10-Jan-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Electrical Works |  |  |  | Pending | Al Andalous Tower 2-MEP | Al Andalous 2 | Corridor | Non-Chargeable
10016068 | 10-Jan-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Electrical Works |  |  |  | Pending | Al Andalous Tower 2-MEP | Al Andalous 2 | Corridor | Non-Chargeable
10016069 | 10-Jan-2026 | P3 | Electrical Works - Electrical - corridor light not working | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Electrical Works |  |  |  | Pending | Al Andalous Tower 2-MEP | Al Andalous 2 | Corridor | Non-Chargeable
10016594 | 31-Jan-2026 | P3 | Andalus2 Roof Top Carpenter is required | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 02-Feb-2026 |  | Ramesh Rajak | Pending | Al Andalous Tower 2-MEP | Al Andalous 2 | Roof Top | Non-Chargeable
Al Andalous Tower 3-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016074 | 10-Jan-2026 | P3 | Andalus3 15th floor, Garbage door issue - Carpenter | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 11-Jan-2026 |  | Ramesh Rajak | Pending | Al Andalous Tower 3-MEP | Al Andalous 3 | Corridor | Non-Chargeable
10016075 | 10-Jan-2026 | P3 | Andalus3 3rd Floor Garbage door issue - Carpenter | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 11-Jan-2026 |  | Ramesh Rajak | Pending | Al Andalous Tower 3-MEP | Al Andalous 3 | Corridor | Non-Chargeable
Al Raffa 1-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016010 | 08-Jan-2026 | P3 | Water Features - Plumbing - Plumbing issues | Saqr Real Estate | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Al Raffa 1-MEP | Reffa 1 | Roof Top | Non-Chargeable
Al Raffa 2-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016292 | 20-Jan-2026 | P3 | Raffa2 Reception Area Electrician is required Watchman phone number - 0556867081 | Askaan Properties LLC | Ousman Seid | Electrical Works |  |  |  | Pending | Al Raffa 2-MEP | Reffa 2 | Corridor | Non-Chargeable
10016341 | 22-Jan-2026 | P3 | Water Features - Plumbing - Drainage blockage Drainage is blocked in Rifaa 2 building | Askaan Properties LLC | Alaa | Plumbing Works |  |  |  | Pending | Al Raffa 2-MEP | Reffa 2 | Ground Floor | Non-Chargeable
Alia plaza-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016279 | 19-Jan-2026 | P3 | Water Features - Plumbing - Plumbing issues | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Alia plaza-MEP | Alia plaza | Entrance | Non-Chargeable
C1 Tower-TFM — 17 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10015979 | 07-Jan-2026 | P3 | Irrigation systems - Sprinklers & emitters - 13mm pipe damages - 307 fire sprinkler damage | Askaan Properties LLC | Arshith Swaminath | Irrigation systems | 07-Jan-2026 | 07-Jan-2026 | AMAANGBC1T2 | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-307 (B) | Non-Chargeable
10015997 | 07-Jan-2026 | P3 | Civil Works - civil - Floor grouting issue | Askaan Properties LLC | Arshith Swaminath | Civil Works | 13-Jan-2026 | 13-Jan-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT 1410 | Non-Chargeable
10015998 | 07-Jan-2026 | P1 | Plumbing systems - Plumbing - Water leakage | Askaan Properties LLC | Arshith Swaminath | Plumbing Works | 08-Jan-2026 | 08-Jan-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT 201 | Non-Chargeable
10016014 | 08-Jan-2026 | P3 | Electrical Works - Electrical - Lift button not working | Askaan Properties LLC | Anas | Electrical Works | 13-Jan-2026 | 13-Jan-2026 | NLTEC1T2 | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Lift Area | Non-Chargeable
10016021 | 08-Jan-2026 | P3 | Civil Works - civil - Floor grouting issue Flat 1512 Wash room need grouting | Askaan Properties LLC | Anas | Civil Works | 13-Jan-2026 | 13-Jan-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1512 (B) | Non-Chargeable
10016022 | 08-Jan-2026 | P3 | Civil Works - civil - Floor grouting issue Flat 2109 Wash room grouting | Askaan Properties LLC | Anas | Civil Works | 13-Jan-2026 | 13-Jan-2026 | Nayan Miah Nurul Hossain | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2109 (B) | Non-Chargeable
10016023 | 08-Jan-2026 | P3 | Water Features - Plumbing - Bath room water heater water leaking. | Askaan Properties LLC | Anas | Plumbing Works | 13-Jan-2026 | 13-Jan-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-307 (B) | Non-Chargeable
10016024 | 08-Jan-2026 | P3 | Electrical Works - Electrical - Electrician required Flat 111 Kitchen electric issue | Askaan Properties LLC | Anas | Electrical Works | 14-Jan-2026 | 14-Jan-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-111 | Non-Chargeable
10016025 | 08-Jan-2026 | P3 | Electrical Works - Electrical - Door Cylinder Repairing Flat 1904 Door cylinder change | Askaan Properties LLC | Anas | Electrical Works | 13-Jan-2026 | 13-Jan-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1904 | Non-Chargeable
10016061 | 10-Jan-2026 | P3 | Water Features - Plumbing - Bath room water heater not working. Flat 210 Water heater not working 0585990715 | Askaan Properties LLC | Anas | Plumbing Works | 13-Jan-2026 | 14-Jan-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT 210 | Non-Chargeable
10016146 | 12-Jan-2026 | P3 | Civil Works - civil - Floor grouting issue | Askaan Properties LLC | Anas | Civil Works | 13-Jan-2026 | 13-Jan-2026 | Nayan Miah Nurul Hossain | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-110 | Non-Chargeable
10016147 | 12-Jan-2026 | P3 | Carpenter works - Carpentry - entrance main door issue | Askaan Properties LLC | Anas | Carpenter works | 13-Jan-2026 | 13-Jan-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1609 (B) | Non-Chargeable
UAT10014144 | 13-Jan-2026 | P3 | Test | Askaan Properties LLC | Kannan Mariappan | Access Control | 13-Jan-2026 |  | Kannan Mariappan | Pending | C1 Tower-TFM | Fortune Residency Tower C1 | APT 1001 | Non-Chargeable
10016221 | 17-Jan-2026 | P3 | Carpenter works - Carpentry - entrance main door issue | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Carpenter works | 11-Feb-2026 | 13-Feb-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10016391 | 23-Jan-2026 | P3 | Fortune c1 main garbage chute satter door not working, | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Carpenter works | 11-Feb-2026 | 15-Feb-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | LV Room | Non-Chargeable
10016392 | 23-Jan-2026 | P3 | 3rd floor garbage chute door not closing | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Carpenter works | 11-Feb-2026 | 15-Feb-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Balcony | Non-Chargeable
10016495 | 27-Jan-2026 | P3 | Carpenter works - Carpentry - Entrance main door machine issue C1 tower main entrance door machine not working need to replace | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Carpenter works | 11-Feb-2026 | 13-Feb-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
Waqef 5-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016293 | 20-Jan-2026 | P3 | Awqaf5 shop#8 Low Water Pressure 0547470419 | Askaan Properties LLC | Ousman Seid | Plumbing Works |  |  |  | Pending | Waqef 5-MEP | AWQAF5 | Shop No 8 | Non-Chargeable
10016598 | 31-Jan-2026 | P3 | Awqaf5 Shop11 Electrical Short 0556480813 | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Electrical Works |  |  |  | Pending | Waqef 5-MEP | AWQAF5 | Shop No 11 | Non-Chargeable

## Feb-2026
A & F Tower-AC — 3 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016939 | 10-Feb-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Askaan Properties LLC | 107-AF | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Office No 107 | Non-Chargeable
10017292 | 18-Feb-2026 | P3 | HVAC systems - Air Conditioner - AC is not cooling | Askaan Properties LLC | 104-AF | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Office No 104 | Non-Chargeable
10017325 | 19-Feb-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Askaan Properties LLC | 104-AF | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Office No 104 | Non-Chargeable
A & F Tower-MEP — 4 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016701 | 03-Feb-2026 | P3 | Water Features - Plumbing - Drainage blockage | Askaan Properties LLC | 105-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 105 | Non-Chargeable
10016851 | 08-Feb-2026 | P3 | Electrical Works - Electrical - Electrician required | Askaan Properties LLC | 101-AF | Electrical Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 101 | Non-Chargeable
10016852 | 08-Feb-2026 | P3 | Water Features - Plumbing - Plumbing issues | Askaan Properties LLC | 101-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 101 | Non-Chargeable
10017314 | 19-Feb-2026 | P3 | Water Features - Plumbing - Plumbing issues | Askaan Properties LLC | 101-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 101 | Non-Chargeable
Al Andalous Tower 1-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016719 | 03-Feb-2026 | P3 | Andalus1 Roof Top Carpenter is required 0502862847 0552064554 | Askaan Properties LLC | Ousman Seid | Carpenter works | 10-Feb-2026 |  | Ramesh Rajak | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Roof Top | Non-Chargeable
10017648 | 28-Feb-2026 | P3 | Andalus1 OTS Water leakage from Pipe Watchman - 0552064554 | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Plumbing Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Roof Top | Non-Chargeable
Al Andalous Tower 2-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016659 | 02-Feb-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Electrical Works |  |  |  | Pending | Al Andalous Tower 2-MEP | Al Andalous 2 | Electrical Room | Non-Chargeable
Al Andalous Tower 3-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016765 | 05-Feb-2026 | P3 | Andalus3 Roof Top Pipe Leakage 0561117136 | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Plumbing Works |  |  |  | Pending | Al Andalous Tower 3-MEP | Al Andalous 3 | Roof Top | Non-Chargeable
Al Raffa 1-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017647 | 28-Feb-2026 | P3 | Raffa1 Outside Area Drainage is blocked Watchman - 0506901476 | Saqr Real Estate | Abdalla Ibrahim Abdelnazir Ibrahim | Plumbing Works |  |  |  | Pending | Al Raffa 1-MEP | Reffa 1 | Ground Floor | Non-Chargeable
Al Raffa 2-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017308 | 19-Feb-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Raffa 2-AC | Reffa 2 | Telephone Room | Non-Chargeable
C1 Tower-TFM — 7 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016725 | 04-Feb-2026 | P1 | Plumbing systems - Plumbing - Water leakage | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Plumbing Works | 10-Mar-2026 | 17-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-807 (B) | Non-Chargeable
10016726 | 04-Feb-2026 | P1 | Plumbing systems - Plumbing - Water leakage | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Plumbing Works | 11-Feb-2026 | 16-Feb-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1405 (B) | Non-Chargeable
10016793 | 06-Feb-2026 | P3 | C1 tower main door machine issue, not closing properly, | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Carpenter works | 11-Feb-2026 | 30-Jun-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Reception | Non-Chargeable
10016810 | 06-Feb-2026 | P3 | C1 tower lift room ac not working | Askaan Properties LLC | Umar Mohideen Pillai Abbas | HVAC systems | 11-Feb-2026 | 13-Feb-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Lift Room | Non-Chargeable
10016846 | 08-Feb-2026 | P3 | Carpenter works - Carpentry - Garbage room door closer not working C1 13th floor garbage room main door not closing | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Carpenter works | 11-Feb-2026 | 16-Feb-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | service room | Non-Chargeable
10016887 | 09-Feb-2026 | P3 | HVAC systems - Air Conditioner - AC is not cooling | Askaan Properties LLC | Umar Mohideen Pillai Abbas | HVAC systems | 11-Feb-2026 | 13-Feb-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Lift Room | Non-Chargeable
10016985 | 11-Feb-2026 | P3 | SMA TV - SMA TV - SMA TV Issue | Askaan Properties LLC | Araki Abasher | SMA TV | 11-Feb-2026 | 27-Feb-2026 | AMAANCCTVC1T2 | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2312 (B) | Non-Chargeable
Najim Building-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016909 | 09-Feb-2026 | P3 | Electrical Works - Electrical - Electrician required | Saqr Real Estate | Arshith Swaminath | Electrical Works |  |  |  | Pending | Najim Building-MEP | Najim Building | Service Room | Non-Chargeable
Nuiymeya 3-Elevator — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017049 | 12-Feb-2026 | P1 | Nuimya3 203 Elevator Stack 4th floor - URGENT 0555410055 | Askaan Properties LLC | 203-NU | Elevater system |  |  |  | Pending | Nuiymeya 3-Elevator | Nuiymeya 3 | Apt No 203 | Non-Chargeable
Waqef 5-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016777 | 05-Feb-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 9 | Non-Chargeable
Waqef 5-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10016944 | 10-Feb-2026 | P3 | Carpenter works - Carpentry - Carpenter required | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 10-Feb-2026 |  | Ramesh Rajak | Pending | Waqef 5-MEP | AWQAF5 | Roof Top | Non-Chargeable

## Mar-2026
A & F Tower-AC — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017775 | 04-Mar-2026 | P1 | AF 1st Floor Ac water leakage URGENT Watchman - 0508983447 | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Corridor | Non-Chargeable
10018932 | 30-Mar-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Askaan Properties LLC | 108-AF | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Office No 108 | Non-Chargeable
A & F Tower-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10018052 | 12-Mar-2026 | P1 | AF 105 Water leakage in the bathroom 0569384511 | Askaan Properties LLC | 105-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 105 | Non-Chargeable
10018308 | 18-Mar-2026 | P3 | AF floor# 3 Carpenter is required | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 24-Mar-2026 | 31-Mar-2026 | Ramesh Rajak | Resolved | A & F Tower-MEP | A&F Tower | Corridor | Non-Chargeable
Al Andalous Tower 1-MEP — 7 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017733 | 04-Mar-2026 | P3 | Andalous1 Watchman room - Roof top Plumber | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Roof Top | Non-Chargeable
10017734 | 04-Mar-2026 | P3 | Andalous1 Watchman room - Roof top Electrician required | Askaan Properties LLC | Arshith Swaminath | Electrical Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Roof Top | Non-Chargeable
10017735 | 04-Mar-2026 | P3 | Andalous1 Watchman room - Roof top Ceiling issue | Askaan Properties LLC | Arshith Swaminath | Carpenter works | 04-Mar-2026 | 31-Mar-2026 | Ramesh Rajak | Resolved | Al Andalous Tower 1-MEP | Al Andalous 1 | Roof Top | Non-Chargeable
10018090 | 14-Mar-2026 | P3 | Andalus1 pump room Carpenter is required 0552064554 | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 14-Mar-2026 | 31-Mar-2026 | Ramesh Rajak | Resolved | Al Andalous Tower 1-MEP | Al Andalous 1 | Transfer Pump Room | Non-Chargeable
10018291 | 18-Mar-2026 | P3 | Andalus 1 building rooftop motor not working, electrician urgent | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Electrical Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Roof Top | Non-Chargeable
10018298 | 18-Mar-2026 | P3 | Electrical Works - Electrical - Light Replacement Andalous1 9th & 4floor Garbage room - Electrician required | Askaan Properties LLC | Arshith Swaminath | Electrical Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Garbage Room | Non-Chargeable
10018507 | 24-Mar-2026 | P3 | Electrical Works - Electrical - Light Replacement Andalous1 Outside Area Light replacement | Askaan Properties LLC | Arshith Swaminath | Electrical Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Entrance | Non-Chargeable
Al Andalous Tower 2-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10018338 | 18-Mar-2026 | P3 | Andloues2 Shop number3 AC not working 0582388714 | Askaan Properties LLC | Walid Ismail Ahmed Dauod | HVAC systems |  |  |  | Pending | Al Andalous Tower 2-AC | Al Andalous 2 | Shop 3 | Non-Chargeable
Al Andalous Tower 3-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10018032 | 12-Mar-2026 | P1 | Plumbing systems - Plumbing - Water leakage | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Al Andalous Tower 3-MEP | Al Andalous 3 | Roof Top | Non-Chargeable
Al Raffa 1-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10018767 | 28-Mar-2026 | P1 | Mashreq Bank Water leakage from Pipe URGENT | Saqr Real Estate | Ahmed Mohammed Abrhim Abdelnazir | Plumbing Works |  |  |  | Pending | Al Raffa 1-MEP | Reffa 1 | Ground Floor | Non-Chargeable
Al Raffa 2-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017992 | 10-Mar-2026 | P3 | Raffa2 Entrance Electrical Trip 0556867081 | Askaan Properties LLC | Ousman Seid | Electrical Works |  |  |  | Pending | Al Raffa 2-MEP | Reffa 2 | Entrance | Non-Chargeable
Al Shaali Building-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10018508 | 24-Mar-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Askaan Properties LLC | G01@injaaz.ae-SH | HVAC systems |  |  |  | Pending | Al Shaali Building-AC | Al Shaali Building | Apt No (G - 01) | Non-Chargeable
Alia plaza-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017991 | 10-Mar-2026 | P3 | Alia plaza - Staircase Staircase Door Repairing | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 14-Mar-2026 | 31-Mar-2026 | Ramesh Rajak | Resolved | Alia plaza-MEP | Alia plaza | Stair Case 1 | Non-Chargeable
Askaan office-LS — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017754 | 04-Mar-2026 | P3 | Askaan Office | Askaan Properties LLC | Walid Ismail Ahmed Dauod | Electrical Works |  |  |  | Pending | Askaan office-LS | Askaan Office | Entrance/ Reception Area | Non-Chargeable
10017758 | 04-Mar-2026 | P3 | Carpenter works - Carpentry - Carpenter required | Askaan Properties LLC | Arshith Swaminath | Carpenter works | 04-Mar-2026 | 31-Mar-2026 | Ramesh Rajak | Resolved | Askaan office-LS | Askaan Office | Entrance/ Reception Area | Non-Chargeable
C1 Tower-TFM — 25 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10017714 | 03-Mar-2026 | P3 | 607 tv signal problem | Askaan Properties LLC | Umar Mohideen Pillai Abbas | SMA TV | 05-Mar-2026 | 09-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-607 (B) | Non-Chargeable
10017715 | 03-Mar-2026 | P3 | C1 exit gate barrier not working, please check urgent | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Gate Barrier | 05-Mar-2026 | 05-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10017928 | 09-Mar-2026 | P3 | Water Features - Plumbing - Plumbing issues | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Plumbing Works | 10-Mar-2026 | 12-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-111 | Non-Chargeable
10017929 | 09-Mar-2026 | P3 | Water Features - Plumbing - Plumbing issues | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Plumbing Works | 10-Mar-2026 | 12-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1812 (B) | Non-Chargeable
10017930 | 09-Mar-2026 | P3 | Water Features - Plumbing - Plumbing issues | Askaan Properties LLC | Arshith Swaminath | Plumbing Works | 10-Mar-2026 | 12-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-110 | Non-Chargeable
10017933 | 09-Mar-2026 | P3 | SMA TV - SMA TV - SMA TV Issue | Askaan Properties LLC | Umar Mohideen Pillai Abbas | SMA TV | 10-Mar-2026 | 14-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-607 (B) | Non-Chargeable
10018002 | 11-Mar-2026 | P3 | Civil Works - civil - Civil Work Required | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Civil Works | 12-Mar-2026 | 17-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2408 | Non-Chargeable
10018024 | 12-Mar-2026 | P3 | Electrical Works - Electrical - Exhausts fan not working Dear Novel team, The elevato's number L3 Excust fan is not working | Askaan Properties LLC | Arshith Swaminath | Electrical Works | 23-Mar-2026 | 24-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10018030 | 12-Mar-2026 | P3 | Electrical Works - Electrical - Gate Barrier Not Working C1 Ground floor exit gate berrior not working, | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Electrical Works | 12-Mar-2026 | 30-Jun-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10018042 | 12-Mar-2026 | P3 | Cleaning - General Services - cleaning C1 flat 110 inside apartment 1BHK cleaning required | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Housekeeping | 12-Mar-2026 | 14-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-110 | Non-Chargeable
10018046 | 12-Mar-2026 | P3 | C1 flat 1910 civil work required | Askaan Properties LLC | 1910-EC | Civil Works | 12-Mar-2026 | 17-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1910 | Non-Chargeable
10018344 | 18-Mar-2026 | P3 | C1 Bravo supermarket breaker tripping, electrician required | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Electrical Works | 23-Mar-2026 | 27-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Back side. | Non-Chargeable
10018345 | 18-Mar-2026 | P3 | Electrical Works - Electrical - Electrical Issue | Askaan Properties LLC | 2308-C | Electrical Works | 23-Mar-2026 | 24-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2308 | Non-Chargeable
10018361 | 22-Mar-2026 | P3 | Electrical Works - Electrical - Electricity tripped C1 Bravo supermarket breaker tripping, electrician required | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Electrical Works | 23-Mar-2026 | 30-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10018376 | 22-Mar-2026 | P3 | SMA TV - SMA TV - SMA TV Issue C1 I check outside satellite working, Issues from apartment inside But not response 607 SMA Tv | Askaan Properties LLC | Umar Mohideen Pillai Abbas | SMA TV | 23-Mar-2026 | 13-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-607 (B) | Non-Chargeable
10018377 | 22-Mar-2026 | P3 | CCTV - CCTV - CCTV screen not working One LCD is not working | Askaan Properties LLC | Umar Mohideen Pillai Abbas | CCTV | 23-Mar-2026 | 24-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | CCTV | Non-Chargeable
10018416 | 22-Mar-2026 | P3 | Carpenter works - Carpentry - Carpenter required | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Carpenter works | 23-Mar-2026 | 24-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1213 | Non-Chargeable
10018425 | 23-Mar-2026 | P3 | CCTV - CCTV - DVR not working LCD of the DVR 13 is out of order, please arrange the team to fix the issue, | Askaan Properties LLC | Umar Mohideen Pillai Abbas | CCTV | 23-Mar-2026 | 24-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | CCTV | Non-Chargeable
10018426 | 23-Mar-2026 | P3 | CCTV - CCTV - Cameras are not working DVR CAMERA 03 - OUTDOOR C5 CAMERA NOT WORKING DVR # 4 - CAMERA P4 C13 NOT WORKING DVR # 2 - CAMERA #15 NOT WORKING Health club Camara #06 also not working DVR#11, LCD fluctuating. | Askaan Properties LLC | Umar Mohideen Pillai Abbas | CCTV | 23-Mar-2026 | 24-Mar-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | CCTV | Non-Chargeable
10018562 | 24-Mar-2026 | P1 | C1 lift 3 rope rusted need to replace | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Elevater system | 09-Apr-2026 | 09-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Lift Area | Non-Chargeable
10018588 | 25-Mar-2026 | P3 | Housekeeping - General Services - cleaning C1 tower HC floor gym machine need to maintenance | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Housekeeping | 09-Apr-2026 | 09-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10018590 | 25-Mar-2026 | P3 | C1 tower HC floor gym machine need to maintenance, | Askaan Properties LLC | Umar Mohideen Pillai Abbas | GYM Equipment | 09-Apr-2026 | 09-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Reception | Non-Chargeable
10018591 | 25-Mar-2026 | P3 | Ground floor outside corridor area light not working | Askaan Properties LLC | Umar Mohideen Pillai Abbas | Electrical Works | 09-Apr-2026 | 09-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Out side area | Non-Chargeable
10018634 | 26-Mar-2026 | P1 | Elevater system - Elevator - Lift is not working | Askaan Properties LLC | Walid Ismail Ahmed Dauod | Elevater system | 09-Apr-2026 | 09-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10018986 | 31-Mar-2026 | P1 | Elevater system - Elevator - Lift is not working Lift3 car gaid roller shoe damaged. Need to replaced. Now lift is under shutdown. | Askaan Properties LLC | Arshith Swaminath | Elevater system | 02-Apr-2026 | 02-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Reception(Back) | Non-Chargeable
Najim Building-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10018350 | 22-Mar-2026 | P3 | Electrical Works - Electrical - Light Replacement Aim spa center light not working | Saqr Real Estate | Anas | Electrical Works |  |  |  | Pending | Najim Building-MEP | Najim Building | Shop No 1 | Non-Chargeable
10018749 | 28-Mar-2026 | P3 | nijam bludging roof toop | Saqr Real Estate | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 28-Mar-2026 | 28-Mar-2026 | Ahmed Mohammed Abrhim Abdelnazir | Resolved | Najim Building-MEP | Najim Building | Roof Top | Non-Chargeable
Waqef 5-AC — 3 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10018173 | 16-Mar-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 1 | Non-Chargeable
10018268 | 17-Mar-2026 | P3 | Awkaf5 shop 8 AC not working 0559748906 | Askaan Properties LLC | Walid Ismail Ahmed Dauod | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 8 | Non-Chargeable
10018961 | 30-Mar-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 10 | Non-Chargeable
Waqef 5-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10018267 | 17-Mar-2026 | P3 | Plumbing Works - Plumbing - Sink Issue | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Waqef 5-MEP | AWQAF5 | Shop No 9 | Non-Chargeable

## Apr-2026
A & F Tower-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020281 | 29-Apr-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | 101-AF | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Office No 101 | Non-Chargeable
A & F Tower-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019203 | 04-Apr-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | 101-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 101 | Non-Chargeable
10020329 | 30-Apr-2026 | P3 | Plumbing Works - Plumbing - Drainage blockage | Askaan Properties LLC | 105-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 105 | Non-Chargeable
Al Andalous Tower 1-MEP — 3 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019198 | 04-Apr-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Entrance | Non-Chargeable
10019676 | 16-Apr-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Entrance | Non-Chargeable
10019686 | 16-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Arshith Swaminath | Electrical Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Entrance | Non-Chargeable
Al Andalous Tower 3-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019846 | 21-Apr-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Andalous Tower 3-AC | Al Andalous 3 | Entrance | Non-Chargeable
Al Raffa 1-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020188 | 28-Apr-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Saqr Real Estate | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Raffa 1-AC | Reffa 1 | Ground Floor | Non-Chargeable
Al Raffa 1-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019578 | 14-Apr-2026 | P3 | Painting - painting - Painter required Raffa1 2nd floor ceiling paint | Saqr Real Estate | Ahmed Mohammed Abrhim Abdelnazir | Painting | 14-Apr-2026 | 15-Apr-2026 | Ahmed Mohammed Abrhim Abdelnazir | Resolved | Al Raffa 1-MEP | Reffa 1 | Corridor | Non-Chargeable
10020027 | 25-Apr-2026 | P3 | Raffa1 Building Complained by Watchman Drainage is blocked 0506901476 | Saqr Real Estate | Abdalla Ibrahim Abdelnazir Ibrahim | Plumbing Works |  |  |  | Pending | Al Raffa 1-MEP | Reffa 1 | Ground Floor | Non-Chargeable
Alia plaza-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019050 | 01-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Arshith Swaminath | Electrical Works |  |  |  | Pending | Alia plaza-MEP | Alia plaza | Stair Case 1 | Non-Chargeable
10019175 | 04-Apr-2026 | P3 | Civil Works - civil - Civil Work Required | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Civil Works | 04-Apr-2026 | 05-Apr-2026 | Ahmed Mohammed Abrhim Abdelnazir | Resolved | Alia plaza-MEP | Alia plaza | Entrance | Non-Chargeable
Askaan office-LS — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019563 | 14-Apr-2026 | P1 | Plumbing Works - Plumbing - Water leakage | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Askaan office-LS | Askaan Office | Archive Room | Non-Chargeable
C1 Tower-TFM — 31 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019051 | 01-Apr-2026 | P1 | Plumbing Works - Plumbing - Water leakage C1 Tower sub pump mechnical seal is damage and water leaking. | Askaan Properties LLC | Mankesh Kumar Singh | Plumbing Works | 02-Apr-2026 | 30-Jun-2026 |  | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area/pump room | Non-Chargeable
10019055 | 01-Apr-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | Arshith Swaminath | Plumbing Works | 02-Apr-2026 | 02-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-612 (B) | Non-Chargeable
10019118 | 02-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 02-Apr-2026 | 02-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10019165 | 04-Apr-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | Mankesh Kumar Singh | Plumbing Works | 04-Apr-2026 | 05-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1904 | Non-Chargeable
10019166 | 04-Apr-2026 | P3 | Carpenter works - Carpentry - Carpenter required | Askaan Properties LLC | Mankesh Kumar Singh | Carpenter works | 04-Apr-2026 | 05-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1904 | Non-Chargeable
10019299 | 06-Apr-2026 | P3 | SMA TV - SMA TV - SMA TV Issue | Askaan Properties LLC | Mankesh Kumar Singh | SMA TV | 13-May-2026 | 13-May-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2312 (B) | Non-Chargeable
10019300 | 06-Apr-2026 | P3 | SMA TV - SMA TV - SMA TV Issue | Askaan Properties LLC | Mankesh Kumar Singh | SMA TV | 13-May-2026 | 13-May-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT- 1202 (B) | Non-Chargeable
10019303 | 06-Apr-2026 | P3 | Plumbing Works - Plumbing - Drainage blockage | Askaan Properties LLC | Mankesh Kumar Singh | Plumbing Works | 06-Apr-2026 | 06-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-513 | Non-Chargeable
10019346 | 07-Apr-2026 | P1 | Plumbing Works - Plumbing - Water leakage | Askaan Properties LLC | Mankesh Kumar Singh | Plumbing Works | 07-Apr-2026 | 07-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2112 (B) | Non-Chargeable
10019347 | 07-Apr-2026 | P3 | Carpenter works - Carpentry - entrance main door issue | Askaan Properties LLC | Mankesh Kumar Singh | Carpenter works | 07-Apr-2026 | 07-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2107 (B) | Non-Chargeable
10019354 | 07-Apr-2026 | P1 | Elevater system - Elevator - Lift is not working Service lift is not working.kindly send the and solve the issue | Askaan Properties LLC | Mankesh Kumar Singh | Elevater system | 07-Apr-2026 | 07-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Back side. | Non-Chargeable
10019409 | 08-Apr-2026 | P3 | Electrical Works - Electrical - Lift button not working - No any screw | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 08-Apr-2026 | 09-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10019424 | 09-Apr-2026 | P3 | Electrical Works - Electrical - Exhausts fan not working Garbage chute exhaust fan not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 09-Apr-2026 | 09-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Roof | Non-Chargeable
10019450 | 11-Apr-2026 | P3 | CCTV - CCTV - Cameras are not working | Askaan Properties LLC | Mankesh Kumar Singh | CCTV | 12-Apr-2026 |  | AMAANCCTVC1T2 | Pending | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
10019451 | 11-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement Bed room light not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 12-Apr-2026 | 13-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2103 | Non-Chargeable
10019485 | 12-Apr-2026 | P3 | Electrical Works - Electrical - corridor light not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 12-Apr-2026 | 13-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10019486 | 12-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement Ground floor entrance area light not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 12-Apr-2026 | 13-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10019487 | 12-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement Gym room light not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 12-Apr-2026 | 13-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10019488 | 12-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement 6th floor corridor light is blinking 12,18th floor light not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 12-Apr-2026 | 13-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10019509 | 13-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement 9 th floor,23rd floor corridor light issue. Parking 3 Tube light not working Ground floor staircase light not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 13-Apr-2026 | 13-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10019539 | 13-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement 12 floor corridor light not working 18 th floor corridor light not working. 9 th floor staircase light not working. 23 Rd floor staircase light not working. Gym room light not working. | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 13-Apr-2026 | 14-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10019633 | 15-Apr-2026 | P3 | Plumbing Works - Plumbing - Drainage blockage | Askaan Properties LLC | Mankesh Kumar Singh | Plumbing Works | 15-Apr-2026 | 15-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1009 (B) | Non-Chargeable
10019695 | 16-Apr-2026 | P3 | Electrical Works - Electrical - corridor light not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 16-Apr-2026 | 17-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | 1st Floor | Non-Chargeable
10019786 | 20-Apr-2026 | P3 | Electrical Works - Electrical - Electrician required | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 20-Apr-2026 | 20-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1014 (B) | Non-Chargeable
10019787 | 20-Apr-2026 | P3 | Electrical Works - Electrical - Mirror light replacement | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 20-Apr-2026 | 21-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-406 | Non-Chargeable
10019879 | 22-Apr-2026 | P3 | Electrical Works - Electrical - Kitchen light not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 22-Apr-2026 | 22-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-1110 | Non-Chargeable
10019880 | 22-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement 13 th floor water meter room no light need electrician | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 22-Apr-2026 | 22-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | service room | Non-Chargeable
10019923 | 22-Apr-2026 | P3 | Electrical Works - Electrical - Light Replacement 8th floor telephone light is not working | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works | 22-Apr-2026 | 22-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | service room | Non-Chargeable
10019952 | 23-Apr-2026 | P1 | Elevater system - Elevator - Lift is not working Lift 4 not working | Askaan Properties LLC | Mankesh Kumar Singh | Elevater system | 23-Apr-2026 | 23-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10020044 | 25-Apr-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | Dennis Serraon Lubay | Plumbing Works | 25-Apr-2026 | 25-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-106 | Non-Chargeable
10020177 | 27-Apr-2026 | P3 | Plumbing Works - Plumbing - Drainage blockage | Askaan Properties LLC | Dennis Serraon Lubay | Plumbing Works | 27-Apr-2026 | 27-Apr-2026 | Dhaneshwar Saphi | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2212 (B) | Non-Chargeable
Najim Building-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020085 | 26-Apr-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Saqr Real Estate | Ahmed Mohammed Abrhim Abdelnazir | HVAC systems |  |  |  | Pending | Najim Building-AC | Najim Building | Ground Floor | Non-Chargeable
Nuiymeya 3-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019576 | 14-Apr-2026 | P3 | Carpenter works - Carpentry - entrance main door issue | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 14-Apr-2026 | 01-May-2026 | Ahmed Mohammed Abrhim Abdelnazir | Resolved | Nuiymeya 3-MEP | Nuiymeya 3 | Entrance | Non-Chargeable
Waqef 5-AC — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019369 | 08-Apr-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 6 | Non-Chargeable
10019679 | 16-Apr-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 1 | Non-Chargeable
Waqef 5-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10019258 | 06-Apr-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Waqef 5-MEP | AWQAF5 | Shop No 6 | Non-Chargeable
10019410 | 08-Apr-2026 | P3 | Civil Works - civil - Ceramic Issue Awkaf5 Alustora salon need to change ceramic | Askaan Properties LLC | Arshith Swaminath | Civil Works | 09-Apr-2026 | 15-Apr-2026 | Ahmed Mohammed Abrhim Abdelnazir | Resolved | Waqef 5-MEP | AWQAF5 | Shop No 1 | Non-Chargeable

## May-2026
A & F Tower-AC — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020931 | 13-May-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Lift Room | Non-Chargeable
10021362 | 22-May-2026 | P1 | AF 15th Ac water leakage 0544617298 | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Stair Case 1 | Non-Chargeable
A & F Tower-MEP — 4 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020395 | 02-May-2026 | P3 | Electrical Works - Electrical - Electrical short | Askaan Properties LLC | 104-AF | Electrical Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 104 | Non-Chargeable
10020512 | 04-May-2026 | P3 | Carpenter works - Carpentry - Window glass broken | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 06-May-2026 |  | Ahmed Mohammed Abrhim Abdelnazir | Pending | A & F Tower-MEP | A&F Tower | Office No 101 | Non-Chargeable
10020978 | 14-May-2026 | P3 | Civil Works - civil - Humidity Issue | Askaan Properties LLC | 106-AF | Civil Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 106 | Non-Chargeable
10021286 | 20-May-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | 105-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 105 | Non-Chargeable
Al Andalous Tower 1-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021060 | 16-May-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Andalous Tower 1-AC | Al Andalous 1 | Lift Room | Non-Chargeable
Al Andalous Tower 1-MEP — 4 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020401 | 02-May-2026 | P3 | Electrical Works - Electrical - Light Replacement - Ground floor corridor, 3rd floor corridor and 7th floor corridor | Askaan Properties LLC | Arshith Swaminath | Electrical Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Entrance | Non-Chargeable
10020818 | 11-May-2026 | P3 | Carpenter works - Carpentry - Garbage door repair work | Askaan Properties LLC | Arshith Swaminath | Carpenter works | 12-May-2026 |  | Ahmed Mohammed Abrhim Abdelnazir | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Corridor | Non-Chargeable
10020869 | 12-May-2026 | P3 | Carpenter works - Carpentry - Electrical room door issue | Askaan Properties LLC | Arshith Swaminath | Carpenter works | 12-May-2026 |  | Ahmed Mohammed Abrhim Abdelnazir | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Electrical Room | Non-Chargeable
10021076 | 16-May-2026 | P3 | Entrance Door Marble Replacement 0504387933 | Askaan Properties LLC | 402-AN1 | Civil Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Entrance | Non-Chargeable
Al Andalous Tower 3-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020770 | 10-May-2026 | P3 | Carpenter works - Carpentry - entrance main door issue | Askaan Properties LLC | Arshith Swaminath | Carpenter works | 12-May-2026 |  | Ahmed Mohammed Abrhim Abdelnazir | Pending | Al Andalous Tower 3-MEP | Al Andalous 3 | Entrance | Non-Chargeable
Al Raffa 1-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020456 | 03-May-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Saqr Real Estate | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Raffa 1-AC | Reffa 1 | Lift Room | Non-Chargeable
Al Raffa 1-MEP — 3 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020491 | 04-May-2026 | P3 | Plumbing Works - Plumbing - Drainage blockage | Saqr Real Estate | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Al Raffa 1-MEP | Reffa 1 | Ground Floor | Non-Chargeable
10021361 | 22-May-2026 | P3 | Raffa1 Building Main Drainage blocked Watchman Contact - 0506901476 | Saqr Real Estate | Ahmed Mohammed Abrhim Abdelnazir | Plumbing Works |  |  |  | Pending | Al Raffa 1-MEP | Reffa 1 | Entrance | Non-Chargeable
10021413 | 23-May-2026 | P3 | Plumbing Works - Plumbing - Drainage blockage Raffa1 Building Main Drainage blocked | Saqr Real Estate | Arshith Swaminath | Plumbing Works |  |  |  | Pending | Al Raffa 1-MEP | Reffa 1 | Ground Floor | Non-Chargeable
Al Raffa 2-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021226 | 19-May-2026 | P3 | Raffa2 twins Caffe Ac is not working 0554149672 Please check | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | Al Raffa 2-AC | Reffa 2 | Ground Floor | Non-Chargeable
Al Raffa 2-MEP — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020723 | 09-May-2026 | P3 | Raffa2 Entrance Dor repairing 0556867081 | Askaan Properties LLC | Ahmed Mohammed Abrhim Abdelnazir | Carpenter works | 09-May-2026 |  | Ahmed Mohammed Abrhim Abdelnazir | Pending | Al Raffa 2-MEP | Reffa 2 | Entrance | Non-Chargeable
10021376 | 22-May-2026 | P3 | Raffa2 Building Main Drainage blocked Watchman Contact | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Plumbing Works |  |  |  | Pending | Al Raffa 2-MEP | Reffa 2 | Entrance | Non-Chargeable
Al Shaali Building-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021450 | 24-May-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Shaali Building-AC | Al Shaali Building | Watchman Room | Non-Chargeable
Alia plaza-MEP — 3 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021564 | 31-May-2026 | P1 | Plumbing Works - Plumbing - Water leakage Aliya plaza water leaking in Garbage room from upper side. | Askaan Properties LLC | Mankesh Kumar Singh | Plumbing Works |  |  |  | Pending | Alia plaza-MEP | Alia plaza | Entrance | Non-Chargeable
10021565 | 31-May-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Mankesh Kumar Singh | Electrical Works |  |  |  | Pending | Alia plaza-MEP | Alia plaza | Entrance | Non-Chargeable
10021617 | 31-May-2026 | P3 | Carpenter works - Carpentry - Carpenter required | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Carpenter works |  |  |  | Pending | Alia plaza-MEP | Alia plaza | Entrance | Non-Chargeable
Askaan office-LS — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020645 | 07-May-2026 | P3 | Askaan Office Ac is not working 067409532 | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | Askaan office-LS | Askaan Office | GM Office | Non-Chargeable
C1 Tower-TFM — 12 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020614 | 06-May-2026 | P3 | Electrical Works - Electrical - corridor light not working | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 06-May-2026 | 06-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10020615 | 06-May-2026 | P3 | Electrical Works - Electrical - Light Replacement Ground floor parking area lights not working | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 06-May-2026 | 06-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking | Non-Chargeable
10020822 | 11-May-2026 | P3 | Electrical Works - Electrical - corridor light not working | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 11-May-2026 | 12-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10020823 | 11-May-2026 | P3 | Civil Works - civil - Tiles issue HC floor staircase area wall tiles | Askaan Properties LLC | Dennis Serraon Lubay | Civil Works | 11-May-2026 | 12-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Rooftop | Non-Chargeable
10020863 | 12-May-2026 | P3 | Electrical Works - Electrical - Booster pump not working | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 12-May-2026 | 13-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10020930 | 13-May-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 13-May-2026 | 13-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor/stair case | Non-Chargeable
10020932 | 13-May-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 13-May-2026 | 13-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor/stair case | Non-Chargeable
10021194 | 19-May-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 19-May-2026 | 19-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10021195 | 19-May-2026 | P3 | Civil Works - civil - Tiles issue 12th floor wall tiles require for repair | Askaan Properties LLC | Dennis Serraon Lubay | Civil Works | 19-May-2026 | 19-May-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor/stair case | Non-Chargeable
10021196 | 19-May-2026 | P3 | Civil Works - Glass Doors - Glass door hinge damaged/malfuctntioning main entrance glass door pivot hinges replacement | Askaan Properties LLC | Dennis Serraon Lubay | Civil Works | 19-May-2026 | 19-May-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10021232 | 19-May-2026 | P1 | Plumbing Works - Plumbing - Water leakage 19th floor corridor area having a leakage from the PPR joints. | Askaan Properties LLC | Dennis Serraon Lubay | Plumbing Works | 21-May-2026 | 02-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10021238 | 19-May-2026 | P3 | Painting - painting - Painter required | Askaan Properties LLC | Dennis Serraon Lubay | Painting | 19-May-2026 | 02-Jun-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor/stair case | Non-Chargeable
Najim Building-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020850 | 12-May-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Saqr Real Estate | Arshith Swaminath | HVAC systems |  |  |  | Pending | Najim Building-AC | Najim Building | Lift Room | Non-Chargeable
Waqef 5-AC — 6 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10020457 | 03-May-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 3 | Non-Chargeable
10020998 | 14-May-2026 | P3 | Awqaf5 Shop#2, Ac is not working 0505353917 | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 2 | Non-Chargeable
10020999 | 14-May-2026 | P3 | Awqaf5 Shop#3 Ac is not working 0505353917 | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 3 | Non-Chargeable
10021000 | 14-May-2026 | P3 | Awqaf5 Shop#4 Ac is not working 0505353917 | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 4 | Non-Chargeable
10021270 | 20-May-2026 | P3 | Awqaf5 Shop 8 Ac cooling and Leakage Issue 0547470419 | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 8 | Non-Chargeable
10021569 | 31-May-2026 | P1 | HVAC systems - Air Conditioner - AC water leakage | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 8 | Non-Chargeable

## Jun-2026
A & F Tower-AC — 4 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10022423 | 14-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | 101-AF | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Office No 101 | Non-Chargeable
10022462 | 16-Jun-2026 | P1 | HVAC systems - Air Conditioner - AC water leakage | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Corridor | Non-Chargeable
10023030 | 25-Jun-2026 | P3 | AF 6th Floor Ac is not working 0552699941 | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Corridor | Non-Chargeable
10023043 | 25-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | 105-AF | HVAC systems |  |  |  | Pending | A & F Tower-AC | A&F Tower | Office No 105 | Non-Chargeable
A & F Tower-MEP — 4 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021664 | 01-Jun-2026 | P3 | Carpenter works - Carpentry - Carpenter required | Askaan Properties LLC | 104-AF | Carpenter works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 104 | Non-Chargeable
10021894 | 04-Jun-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | 105-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 105 | Non-Chargeable
10022559 | 17-Jun-2026 | P3 | Electrical Works - Electrical - Electrician required | Askaan Properties LLC | 101-AF | Electrical Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 101 | Non-Chargeable
10023044 | 25-Jun-2026 | P3 | Plumbing Works - Plumbing - Plumbing issues | Askaan Properties LLC | 105-AF | Plumbing Works |  |  |  | Pending | A & F Tower-MEP | A&F Tower | Office No 105 | Non-Chargeable
Al Andalous Tower 1-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021630 | 01-Jun-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Arshith Swaminath | Electrical Works |  |  |  | Pending | Al Andalous Tower 1-MEP | Al Andalous 1 | Garbage Room | Non-Chargeable
Al Andalous Tower 3-MEP — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10023286 | 29-Jun-2026 | P1 | Plumbing Works - Plumbing - Water leakage | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | Plumbing Works |  |  |  | Pending | Al Andalous Tower 3-MEP | Al Andalous 3 | Roof Top | Non-Chargeable
Al Raffa 1-AC — 4 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021742 | 02-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Saqr Real Estate | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Raffa 1-AC | Reffa 1 | Ground Floor | Non-Chargeable
10021786 | 02-Jun-2026 | P3 | R1 Telephone room ac not working | Saqr Real Estate | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Al Raffa 1-AC | Reffa 1 | Telephone Room | Non-Chargeable
10022084 | 08-Jun-2026 | P1 | HVAC systems - Air Conditioner - AC water leakage | Saqr Real Estate | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Raffa 1-AC | Reffa 1 | Ground Floor | Non-Chargeable
10022457 | 16-Jun-2026 | P1 | HVAC systems - Air Conditioner - AC water leakage | Saqr Real Estate | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Al Raffa 1-AC | Reffa 1 | Corridor | Non-Chargeable
Al Raffa 1-Elevator — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10022593 | 18-Jun-2026 | P1 | Elevater system - Elevator - Lift is not working | Saqr Real Estate | Alaa | Elevater system |  |  |  | Pending | Al Raffa 1-Elevator | Reffa 1 | Ground Floor | Non-Chargeable
Al Raffa 2-AC — 4 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021643 | 01-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Raffa 2-AC | Reffa 2 | Lift Room | Non-Chargeable
10021822 | 03-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC filter cleaning Raffa2 shop1 AC filter cleaning 0554149672 | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Raffa 2-AC | Reffa 2 | Ground Floor | Non-Chargeable
10021966 | 05-Jun-2026 | P3 | Raffa2 Twins Caffee Ac is not working 0554149672 | Askaan Properties LLC | Ousman Seid | HVAC systems |  |  |  | Pending | Al Raffa 2-AC | Reffa 2 | Ground Floor | Non-Chargeable
10022782 | 22-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC is not working Raffa2 Lift room, Telephone room 10th floor corridor | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Al Raffa 2-AC | Reffa 2 | Lift Room | Non-Chargeable
Al Shaali Building-AC — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10022735 | 21-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Al Shaali Building-AC | Al Shaali Building | Watchman Room | Non-Chargeable
Askaan office-LS — 1 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021884 | 04-Jun-2026 | P3 | Askaan Office Electrician is required 067409532 | Askaan Properties LLC | Ousman Seid | Electrical Works |  |  |  | Pending | Askaan office-LS | Askaan Office | Entrance/ Reception Area | Non-Chargeable
C1 Tower-TFM — 18 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10022093 | 08-Jun-2026 | P3 | Electrical Works - Electrical - Light Replacement Ground floor parking lights not working | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 08-Jun-2026 | 11-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
10022094 | 08-Jun-2026 | P3 | Carpenter works - Carpentry - Main Door Issue 15th floor staircase door closer not working properly | Askaan Properties LLC | Dennis Serraon Lubay | Carpenter works | 08-Jun-2026 | 11-Jun-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor/stair case | Non-Chargeable
10022095 | 08-Jun-2026 | P3 | Electrical Works - Electrical - Gate Barrier Not Working Gate barrier main entrance fixed the access card machine | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 08-Jun-2026 | 11-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
10022096 | 08-Jun-2026 | P3 | Civil Works - civil - Tiles issue Parking 1 skirt wall tiles removed Parking 3 skirt wall tiles removed | Askaan Properties LLC | Dennis Serraon Lubay | Civil Works | 08-Jun-2026 | 11-Jun-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
10022097 | 08-Jun-2026 | P3 | Civil Works - civil - Tiles issue Health club skirt wall tiles removed | Askaan Properties LLC | Dennis Serraon Lubay | Civil Works | 08-Jun-2026 | 11-Jun-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Exit/ Entry | Non-Chargeable
10022271 | 11-Jun-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 11-Jun-2026 | 11-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
10022277 | 11-Jun-2026 | P3 | Carpenter works - Carpentry - entrance main door issue | Askaan Properties LLC | Dennis Serraon Lubay | Carpenter works | 11-Jun-2026 | 11-Jun-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
10022278 | 11-Jun-2026 | P3 | Electrical Works - Electrical - corridor light not working | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 11-Jun-2026 | 11-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10022600 | 18-Jun-2026 | P3 | Plumbing Works - Plumbing - Drainage blockage Having a drainage blockage from 103,104,105,106 and 107 from P4 drainage line | Askaan Properties LLC | Dennis Serraon Lubay | Plumbing Works | 20-Jun-2026 | 23-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-103 | Non-Chargeable
10022601 | 18-Jun-2026 | P3 | Electrical Works - Electrical - Light Replacement | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 20-Jun-2026 | 23-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10022602 | 18-Jun-2026 | P3 | Civil Works - civil - Tiles issue Parking 4 wall tiles issue | Askaan Properties LLC | Dennis Serraon Lubay | Civil Works | 20-Jun-2026 | 30-Jun-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
10022604 | 18-Jun-2026 | P3 | Electrical Works - Electrical - Light Replacement 25th floor garbage room lights issue | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 20-Jun-2026 | 23-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10022605 | 18-Jun-2026 | P3 | Electrical Works - Electrical - Light Replacement Parking 1 tube lights not working | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 20-Jun-2026 | 23-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
10023065 | 26-Jun-2026 | P1 | 2214 water leaking from kitchen ceiling | Askaan Properties LLC | 2214-EC | Plumbing Works | 26-Jun-2026 | 30-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | APT-2214 (B) | Non-Chargeable
10023094 | 26-Jun-2026 | P3 | C1 Reception Area Ac is not working | Askaan Properties LLC | Dennis Serraon Lubay | HVAC systems | 28-Jun-2026 | 30-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Reception | Non-Chargeable
10023325 | 30-Jun-2026 | P3 | 2nd floor corridor lights replacement | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 30-Jun-2026 | 30-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Corridor | Non-Chargeable
10023326 | 30-Jun-2026 | P3 | GF lights replacement | Askaan Properties LLC | Dennis Serraon Lubay | Electrical Works | 30-Jun-2026 | 30-Jun-2026 | Mustafa Shaik | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Reception | Non-Chargeable
10023327 | 30-Jun-2026 | P3 | Parking 1 wall tiles repaired | Askaan Properties LLC | Dennis Serraon Lubay | Civil Works | 30-Jun-2026 | 30-Jun-2026 | Abdul Raouf | Resolved | C1 Tower-TFM | Fortune Residency Tower C1 | Parking area | Non-Chargeable
Najim Building-AC — 2 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021785 | 02-Jun-2026 | P3 | Najem Watchman room ac complain | Saqr Real Estate | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Najim Building-AC | Najim Building | Ground Floor | Non-Chargeable
10022736 | 21-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Saqr Real Estate | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Najim Building-AC | Najim Building | Corridor | Non-Chargeable
Waqef 5-AC — 7 Non-Chargeable Work Order(s)
WorkOrder No | Reported Date | Priority | Work Description | Client | Reported By | Service Group | Assigned Date | Work Start Date | Closed By | Status | Contract | Zone | BaseUnit | Space
10021720 | 02-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 5 | Non-Chargeable
10021731 | 02-Jun-2026 | P1 | HVAC systems - Air Conditioner - AC water leakage | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 5 | Non-Chargeable
10021779 | 02-Jun-2026 | P3 | Awqaf5 Shop 6 Ac is not working 0552647249 | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 6 | Non-Chargeable
10022226 | 10-Jun-2026 | P1 | Awqaf5 shop8 AC water leakage 0526487987 | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 8 | Non-Chargeable
10022665 | 20-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC Issue | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | WatchMan Room | Non-Chargeable
10022822 | 23-Jun-2026 | P3 | HVAC systems - Air Conditioner - AC is not working | Askaan Properties LLC | Arshith Swaminath | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 7 | Non-Chargeable
10022952 | 24-Jun-2026 | P3 | Awqaf5 Shop 12 Ac is not working 0505353917 | Askaan Properties LLC | Abdalla Ibrahim Abdelnazir Ibrahim | HVAC systems |  |  |  | Pending | Waqef 5-AC | AWQAF5 | Shop No 1 | Non-Chargeable